## SHeikh and Abbas Tasks
Point | Assignee | Accountable | Priority | Risk? | Update | Update Date | Target Date | Status | Completion | Area | Type | Remarks
Customers Engagement App Mobile App Contents - Action to review | Mohamed M. Abbas | Mohammed A. Shahnawaz | High |  | Weekly | 2023-08-21 | 2023-10-01 | UAT | 80%
Chatbot - nearest location | Mohamed M. Abbas | Mohammed A. Shahnawaz | High |  | Weekly | 2023-08-29 | 2023-08-31 | In progress | 30%
CRM Integration with MoE | Mohamed M. Abbas | Mohammed A. Shahnawaz | High | Yes | Daily | 2023-08-21 | 2023-08-31 | UAT | 90% |  |  | To be discussed with Shiekh after he is back from vacation.
Call Center Project status | Mohamed M. Abbas | Mohammed A. Shahnawaz | High |  | Daily | 2023-08-29 | 2023-06-29 | Not Started | 80% |  |  | Waiting for IST feedback and action
Business Rules: CX | Mohamed M. Abbas | Mohammed A. Shahnawaz | High |  | Weekly | 2023-08-21 | 2023-08-31 | In progress | 10%
Nafath Integeration | Mohamed M. Abbas | Mohammed A. Shahnawaz | High |  | Weekly | 2023-08-29 | 2023-08-31 | In progress | 60% |  |  | Cost per transaction (6 SAR for Nafath + 2 SAR for National Address) to be reviewed by business.
Intergration issued has been solved
Mobile Control for Sales Operations | Mohamed M. Abbas | Mohammed A. Shahnawaz | High |  | Weekly | 2023-08-21 | 2023-08-31 | In progress | 10% |  |  | Abbas to update / Abbas asking for more clarification
Control Room (Release 3 Requirments) | Mohamed M. Abbas | Mohammed A. Shahnawaz | High |  | Weekly | 2023-08-21 | 2023-08-31 | In progress | 10% |  |  | Dicussion going on with Improva team to start the work. / Waiting for PO
CRM Integration with MoE | Mohamed M. Abbas | Mohammed A. Shahnawaz | High |  | Weekly | 2023-08-21 | 2023-08-31 | UAT | 80% |  |  | MoE to share the updated BRD
Price Board Printing on GASCO Internet Website | Mohamed M. Abbas | Mohammed A. Shahnawaz | High |  | Weekly | 2023-08-21 | 2023-10-01 | UAT | 85% |  |  | Video Sent to Anas, Waiting for MoE confirmation to deploy.
Price dropdown list on GASCO Internet Website | Mohamed M. Abbas | Mohammed A. Shahnawaz | High |  | Weekly | 2023-08-21 | 2023-10-01 | UAT | 85% |  |  | Video Sent to Anas, Waiting for MoE confirmation to deploy.
Commercial registration (Wathq) | Mohamed M. Abbas | Mohammed A. Shahnawaz | Low |  | Weekly | 2023-08-21 | 2023-07-31 | On Hold | 0% |  |  | Abdullah Al-Khaldi from Complaince needs to contact Nafth regarding this.
Complaint - Customer App | Mohamed M. Abbas | Mohammed A. Shahnawaz | Low |  | Weekly | 2023-08-21 | 2023-07-31 | Not started | 0% |  |  | Not yet assigned
Customer Tracker Timeline | Mohamed M. Abbas | Mohammed A. Shahnawaz | Low |  | Weekly | 2023-08-21 | 2023-07-31 | Not started | 0% |  |  | Not yet assigned
Nafath fees exemption email to be sent | Mohamed M. Abbas | Mohammed A. Shahnawaz | Low |  | Weekly | 2023-08-21 | 2023-07-31 | On Hold | 0% |  |  | Abdullah Al-Khaldi from Complaince needs to contact Nafth regarding this.
Distributor: Daily report of open order from distributor with againg | Mohamed M. Abbas | Mohammed A. Shahnawaz | Medium |  | Daily | 2023-08-21 | 2023-08-31 | UAT | 80% |  |  | To be discussed with Shiekh after he is back from vacation.
customer application - driver follow up link : From the customer application send to the customer message link to follow the driver on map for about 30Min and then make it expired. | Mohamed M. Abbas | Mohammed A. Shahnawaz | Medium | Yes | Weekly | 2023-08-29 | 2023-08-30 | Not started | 0% |  |  | Need Business Requirments and approval to check the posibility in AVL integeration. / still checking the feasiblity
Distributor: review the distributor cycle | Mohamed M. Abbas | Mohammed A. Shahnawaz | Medium |  | Daily | 2023-08-29 | 2023-07-31 | In progress | 60% |  |  | To be discussed with Shiekh after he is back from vacation.
اعتماد الهوية الوطنية كوثيقة اثبات هوية حاملها بالوثيقة المطبوعة | Mohamed M. Abbas | Mohammed A. Shahnawaz | Medium |  | Monthly | 2023-08-21 | 2023-08-30 | Not started | 0% |  |  | Abbas to update
Citrix Integration with MoE | Mohamed M. Abbas | Mohammed A. Shahnawaz | Medium |  | Weekly | 2023-08-21 | 2023-07-31 | Not Started | 0% |  |  | Need to check with MoE is there in Citrix
Sync Time Zones: for all systems (All SAP, Non-SAP, AD, …etc.) | Mohamed M. Abbas | Mohammed A. Shahnawaz | Medium |  | Weekly | 2023-08-21 | 2023-08-31 | In progress | 30% |  |  | Sheikh Ali AKhtar following up with the team and in process.
Cylinder Inspection Based on AI Technology | Mohamed M. Abbas | Mohammed A. Shahnawaz | Medium |  | Weekly | 2023-08-29 | 2023-08-31 | In progress | 5% |  |  | Discussion initiated with a vendor proven consult and waiting for the discovery report. / Still in scope phase RFP tp be puplished
CX: Channels statistics report | Mohamed M. Abbas | Mohammed A. Shahnawaz | High |  | Weekly | 2023-08-21 | 2023-08-31 | In progress | 10% |  |  | Sheikh discussing with Abbas for access and then he will work on it.
ربط شكاوي العملاء بوزارة الطاقة | Mohamed M. Abbas | Mohammed A. Shahnawaz | High |  | Weekly | 2023-08-29 | 2023-08-31 | In progress | 40% |  |  | In progress with MOE.
Trans. Company & Bulk: To ensure all type of controls moved to the new company codes for each process existing in Gasco. | Mohamed M. Abbas | Mohammed A. Shahnawaz | High |  | Weekly | 2023-08-21 | 2023-08-31 | In progress | 30% |  |  | Will be a task as with BDC Project progressing
(Secure Configuration and Hardening) - APIs - Pen Test | Mohamed M. Abbas | Mohammed A. Shahnawaz | Critical |  | Daily | 2023-08-21 | 2023-08-31 | In progress | 15% |  |  | To be discussed with Shiekh after he is back from vacation.
CX Channels reveiw : Saja - Abbas | Mohamed M. Abbas | Mohammed A. Shahnawaz | High |  | Daily | 2023-08-29 | 2023-08-31 | In progress | 60% |  |  | Initial demo to be scheduled / initial demo done / and Workshops to be started from coming sunday
SADAD : BGDC | Mohamed M. Abbas | Mohammed A. Shahnawaz | High |  | Weekly | 2023-08-29 | 2023-08-31 | In progress | 80% |  |  | In testing pipeline with SADAD.
Sync Time Zones: Sync Time Zones b/w C4C-PIPO¦CPI-S/4 | Mohamed M. Abbas | Mohammed A. Shahnawaz | Critical |  | Daily | 2023-08-21 | 2023-08-31 | In progress | 10% |  |  | To be discussed with Shiekh after he is back from vacation.
Sync Time Zones:All Channels (IVR, Distributor Portal, Customers Mobile App, Customers Portal | Mohamed M. Abbas | Mohammed A. Shahnawaz | Critical |  | Daily | 2023-08-21 | 2023-08-31 | In progress | 10% |  |  | To be discussed with Shiekh after he is back from vacation.
Unifonic accounts list | Mohamed M. Abbas | Mohammed A. Shahnawaz | High |  | Daily | 2023-08-29 | 2023-08-31 | In progress | 30% |  |  | Mohammed Abbas in touch with Unifonic to get this done.
Customer Engagement | Mohamed M. Abbas | Mohammed A. Shahnawaz | High